## Task-Tracker
Task ID | Task Name | Assigned To | Priority | Status | Deadline | Progress %
T01 | Write BRD for Contact Page | You (Lead) | High | Done | 2026-10-07 | 100%
T02 | Audit About Us content | You | High | Done | 2026-10-07 | 100%
T03 | Audit Services content | Rahul | Medium | To Do | 2026-10-07 | 0%
T04 | Test Contact Form | You | High | To Do | 2026-10-08 | 0%
T05 | Check Mobile View | Priya | Medium | To Do | 2026-10-08 | 0%
T06 | Bug Reporting | Priya | Medium | To Do | 2026-10-08 | 0%
T07 | Create QA Dashboard | You | High | To Do | 2026-10-08 | 0%
T08 | Daily Standup 15min | All | Low | Daily | Daily | 0%
T09 | Final Review | You (Lead) | High | To Do | 2026-10-08 | 0%
T10 | Push to GitHub | You | Medium | To Do | 2026-10-08 | 0%

## Dashboard
Metric | Value
Total Test Cases | 15
Passed | 11
Failed | 3
Pending | 1
Pass % | 73%
Total Bugs | 4
High | 1
Medium | 1
Low | 2

## Content-Audit
ID | Page | Original Text | AI Version | Issues Found | Final Corrected
C01 | About Us | EpicMinds IT is a leading provider of innovative IT solutions | We are a top IT company providing innovative solutions | Buzzword, repetitive | EpicMinds IT delivers custom software and digital solutions for startups
C02 | Services | We provide best in class services for our clients | We offer world-class services to our clients | Generic, no specifics | We build Websites, Mobile Apps, Cloud and QA services tailored to needs
C03 | Careers | Join our team and grow your career | Become part of our dynamic team | Too vague | Hiring Developers QA BA - Growth, live projects, learning. Apply via form

## Test-Cases
Test ID | Module | Test Scenario | Steps | Expected | Result
TC_01 | Contact Form | Valid submit | Enter valid data + submit | Success message | Pass
TC_02 | Contact Form | Invalid email | Enter abc@ + submit | Error message | Fail - BUG
TC_03 | Contact Form | Empty fields | Leave blank + submit | Required error | -
TC_04 | Navigation | Header links | Click all menus | Navigate correctly | -
TC_05 | Mobile | Homepage mobile | Open 375px width | No layout break | -
TC_06 | Footer | Social icons | Click LinkedIn | Opens company profile | -
TC_07 | Performance | Load time | Open home on 4G | <3 sec load | -
TC_08 | Logo | Logo click | Click logo anywhere | Goes to home | -
TC_09 | Careers | Apply button | Click Apply | Form opens | -
TC_10 | Content | Spelling check | Read About Us page | No mistakes | -
TC_11 | Images | Broken images | Scroll full site | All images load | -
TC_12 | 404 | Invalid URL | Go to /xyz123 | Show 404 page | -
TC_13 | Form | Phone clickable | Click phone number | Dialer opens | -
TC_14 | SEO | Title tag | Check browser tab title | Proper title shown | -
TC_15 | Security | SQL test | Enter ' OR 1=1 in form | Should block it | -

## Bug-Report
Bug ID | Title | Severity | Steps | Expected | Actual | Status
BUG_01 | Contact form accepts abc@ | High | Contact > type abc@ > Submit | Should show email error | Form submitted | Open
BUG_02 | Mobile menu text overlap | Medium | Open site <400px width | Readable menu | Text overlapping | Open
BUG_03 | LinkedIn footer goes to generic | Low | Click footer LinkedIn icon | Company LinkedIn page | Goes to LinkedIn home | Open
BUG_04 | Footer Social Links Open in Same Tab | low | 1.Go to footer 2. Click Instagram icon 3. It opens | Should open in new tab | Opens in same tab | open